## Sheet1
# | Modules | Features | Tasks | Frontend (Responsive) (man-hour) | Backend (man-hour) | QA (man-hour) | Total (man-hour)
1 | Project Initialization, Requirement Analysis & Planning |  |  | 1.6 | 22.4 | 0 | 24
|  | Requirement Analysis | Read the BID end to end, research recruitment domain and candidate technologies (video, STT, CV parsing) ✓ Read the BID end to end and highlight ambiguous, incomplete or conflicting requirements (e.g., duration figures, job-post text in the scope table) ✓ Research the recruitment and interview domain: screening criteria, structured interview evaluation, common bias risks ✓ Survey options per layer: WebRTC approach, speech-to-text with diarisation, CV parsing (PDF/DOCX/OCR), embeddings and vector store, LLM provider ✓ Record findings and a shortlist per layer in the research notes | 0 | 6 | 0 | 6
|  |  | Raise clarification questions, record trainer answers and adopted assumptions ✓ Group questions by theme: scope, data, technology, evaluation, AI usage ✓ Raise the questions with the trainer and record answers as received ✓ Write down assumptions adopted wherever no answer was given ✓ Commit the clarification document to /docs | 0 | 4 | 0 | 4
|  | Solution Design | High-level architecture and component diagram, stack justification ✓ Draw the component diagram: frontend, FastAPI, agent layer, speech-to-text, database, vector store, LLM ✓ Define the data flow across the three stages (pre-, during-, post-interview) ✓ Justify each technology choice, including the frontend framework ✓ Note any local-development exceptions to secure transport | 0.8 | 3.2 | 0 | 4
|  |  | LangGraph agent design (state, nodes, edges) for screening, Q&A analysis, assessment ✓ Define the shared state schema for each graph ✓ List nodes with their purpose, plus edges, conditional routes and retry/error paths ✓ Design three graphs: CV screening, Q&A analysis, consolidated assessment ✓ Document what state flows between nodes | 0 | 3.2 | 0 | 3.2
|  |  | Project name, positioning statement, rationale ✓ Shortlist product names and test each against the problem and audience ✓ Write the one-line positioning statement (what it does, for whom) ✓ Write the 2-4 sentence rationale for the chosen name ✓ Plan consistent use across repo, README, UI and slides | 0.8 | 1.2 | 0 | 2
|  | Planning | WBS with estimates and dependencies, 17-day plan, risk register ✓ Decompose scope to task level with effort, dependencies and definition of done ✓ Sequence the 17 development days against milestones M1-M7 ✓ Build the risk register (video pipeline, diarisation, CV parsing, rate limits, clean-machine Docker) with likelihood, impact, mitigation ✓ Complete without AI assistance (NA1) | 0 | 4 | 0 | 4
|  |  | Initialise GitHub repo (structure, README skeleton, .gitignore, .env.example) ✓ Create the repo structure: backend/, frontend/, docs/, tests/, test-data/ ✓ Add .gitignore covering CVs, recordings, transcripts, DB, .env, virtual environments, IDE files ✓ Add .env.example with placeholders and a README skeleton with all required headings ✓ Share the repo with the trainer team and make the first commit | 0 | 0.8 | 0 | 0.8
2 | Foundation & Environment Setup |  |  | 2 | 12.8 | 1.2 | 16
|  | Backend & Environment | FastAPI skeleton with health endpoint and OpenAPI docs ✓ Set up project layout: routers, services, schemas, agents, core config ✓ Add a health endpoint and a config loader reading environment variables ✓ Create base Pydantic schemas and a standard error model that leaks no stack traces or paths ✓ Confirm OpenAPI docs at /docs and set up structured logging | 0 | 2 | 0.4 | 2.4
|  |  | Dockerfiles, Docker Compose, named volumes, environment configuration ✓ Write Dockerfiles for backend and frontend on slim base images with a .dockerignore ✓ Write docker-compose.yml with services, network, dependencies and health checks ✓ Define named volumes for the database and uploads ✓ Document build, run, stop and reset commands in the README | 0 | 2.8 | 0.4 | 3.2
|  |  | Database schema and models (job profile, candidate, CV, score, session, transcript, assessment) ✓ Choose the database and model entities: job profile, candidate, CV, parsed attributes, score, session, transcript turn, Q&A pair, assessment ✓ Define relationships and identifiers ✓ Create migrations and a seed script ✓ Verify data survives a container restart | 0 | 2.4 | 0 | 2.4
|  | CV Ingestion | CV upload with file type and size validation ✓ Build single and batch upload endpoints (multipart) ✓ Validate extension, MIME type and size; reject anything else with a clear message ✓ Store files under generated names outside the web root ✓ Build the upload UI with per-file progress and status | 0.8 | 0.8 | 0 | 1.6
|  |  | CV parser for PDF (DOCX encouraged) with fail-safe handling for bad layouts ✓ Extract PDF text, including multi-column layouts; add DOCX support ✓ For scanned or image-heavy files, flag as low quality instead of crashing ✓ Wrap each file in error handling so a failure is logged and skipped, not fatal to the batch ✓ Test on all 20 sample CVs plus synthetic edge cases | 0 | 2.8 | 0.4 | 3.2
|  | Agent & Risk Spike | Base LangGraph state definition and scaffold graph ✓ Define the typed graph state and one placeholder node ✓ Compile the graph and expose an invocation wrapper callable from FastAPI ✓ Decide how state is checkpointed between steps | 0 | 0.8 | 0 | 0.8
|  |  | Risk spike: WebRTC audio/video prototype between two browsers ✓ Build minimal WebSocket signalling ✓ Exchange audio and video between two browser tabs ✓ Capture a separate audio track per participant ✓ Record findings and decide keep or fallback before Day 9 | 1.2 | 1.2 | 0 | 2.4
3 | Pre-Interview: CV Screening, Ranking & Scoring - F1, F2 |  |  | 6 | 14 | 4 | 24
|  | Job Requirement Profile | Create / edit job requirement profile (required and preferred skills, qualifications, min. experience, dimension weights) ✓ Define fields: title, required skills, preferred skills, qualifications, minimum years, additional criteria ✓ Add dimension weights (technical, experience, qualifications) validated to total 100 ✓ Build CRUD endpoints with Pydantic validation ✓ Build the form UI to create, edit and reload profiles | 2.4 | 0.8 | 0.4 | 3.6
|  | CV Screening & Ranking (F1) | Structured extraction node (LLM to Pydantic schema: contact, education, work history, skills, certifications, projects) ✓ Define the CV schema: contact, education, work history, skills, certifications, projects ✓ Prompt for structured output, validate it, retry on malformed responses ✓ Keep protected characteristics (age, gender, nationality, etc.) out of fields used for scoring ✓ Persist the parsed record per CV | 0 | 2.4 | 0.4 | 2.8
|  |  | Semantic CV-to-requirement matching with evidence extraction ✓ Embed requirements and CV sections (or compare with the LLM) ✓ Map each requirement to its best evidence passage with a confidence value ✓ Handle synonyms and implied skills (e.g., Django implies Python web development) ✓ Store the evidence quote and its location in the CV | 0 | 3.2 | 0.8 | 4
|  |  | Met / partially met / unmet mapping with CV evidence ✓ Define the rubric and thresholds for met, partially met and unmet ✓ Classify every requirement and attach its evidence ✓ Flag requirements with no evidence in the CV ✓ Write tests against CVs with known expected outcomes | 0 | 1.6 | 0.4 | 2
|  |  | Batch screening pipeline: async execution, status endpoint, retry and error edges in graph ✓ Run a batch as a background job with a job ID ✓ Add graph error edges: retry with backoff, then skip and mark the CV failed ✓ Expose a status endpoint (queued, running, done, failed counts) ✓ Handle rate limits and cache results to avoid re-running work | 0 | 2.4 | 0.8 | 3.2
|  |  | Screening and ranking UI with per-candidate drill-down ✓ Show a ranked table with score and met/partial/unmet counts ✓ Add a drill-down with evidence quotes per requirement ✓ Show progress while running and a clear message for failed CVs ✓ Add sorting and filtering | 3.2 | 0 | 0.4 | 3.6
|  | Candidate Scoring (F2) | Multi-dimension scoring (technical, experience, qualifications) with configurable weights and justifications ✓ Score technical skills, experience and qualifications on a 0-100 rubric ✓ Apply the profile's weights to compute the aggregate ✓ Generate a short justification for each dimension citing CV evidence ✓ Display aggregate and breakdown in the UI | 0.4 | 2.4 | 0.4 | 3.2
|  |  | Reproducibility controls (temperature 0, caching, structured outputs) ✓ Set temperature to 0 and version the prompts ✓ Cache results by CV hash plus profile hash ✓ Repeat-run five CVs and record the score variance | 0 | 0.8 | 0.4 | 1.2
|  |  | Persist scores and record measured batch time for README (N1) ✓ Save score, breakdown, justification and prompt version ✓ Add a retrieval endpoint for later merging into the assessment ✓ Time a 20-CV batch and record the figure for the README (N1) | 0 | 0.4 | 0 | 0.4
4 | During-Interview: AI Video Interview - F3 |  |  | 8.8 | 12 | 3.2 | 24
|  | Session Management | Signalling server (WebSocket) and session lifecycle API (create, join, conduct, end) ✓ Implement WebSocket signalling (offer, answer, ICE) with one room per session ✓ Add create, join and end endpoints with session status states ✓ Configure STUN and note TURN limitations for local use ✓ Handle second-participant join and duplicate joins | 0 | 4 | 0.8 | 4.8
|  |  | Session setup: link session to candidate and job profile ✓ Let the interviewer pick a candidate and a job profile ✓ Generate a separate join link for each role ✓ Persist the session-to-candidate-to-profile link ✓ Validate that both records exist before creating the session | 1.6 | 1.2 | 0 | 2.8
|  |  | Role separation: interviewer vs candidate access ✓ Issue role-scoped tokens (interviewer, candidate) and check them on every endpoint ✓ Show the candidate only the interview room ✓ Test that a candidate token gets 403 on scoring, ranking and assessment endpoints | 0 | 2 | 0.4 | 2.4
|  |  | Persist session record (start/end times, participants) ✓ Store start time, end time, participants, status and duration ✓ Auto-end sessions after a disconnect timeout ✓ Verify records survive a restart | 0 | 0.8 | 0 | 0.8
|  | Video Interface | Browser video/audio room with mute, camera toggle and end-session controls ✓ Use getUserMedia to show local and remote video tiles ✓ Add mute, camera toggle and end-session controls ✓ Show clear messages for denied permissions or missing devices ✓ Make the layout responsive | 4.8 | 0 | 0.8 | 5.6
|  |  | Continuous per-participant audio capture and streaming to backend ✓ Capture a separate microphone stream per participant in short chunks (1-3 s) ✓ Stream chunks over WebSocket with participant ID and time offset ✓ Buffer chunks on the backend temporarily ✓ Verify continuous capture in a 10+ minute session | 1.6 | 2.4 | 0.4 | 4.4
|  |  | Reconnect and network-drop handling ✓ Reconnect WebSocket and ICE automatically with backoff ✓ Buffer audio chunks on the client while offline and resend on reconnect ✓ Keep the transcript captured so far when a connection drops ✓ Test by toggling the network mid-session | 0.8 | 1.6 | 0.8 | 3.2
5 | During-Interview: Speech Recognition & Transcription - F4 |  |  | 2.4 | 10.8 | 2.8 | 16
|  | Transcription Pipeline | Speech-to-text integration (streaming or chunked) ✓ Choose the speech-to-text service and wrap it behind an interface ✓ Stream chunks and handle partial versus final results ✓ Set language to English and add timeouts and retries ✓ Measure and record transcription latency | 0 | 4 | 0.8 | 4.8
|  |  | Speaker attribution via channel separation (diarisation as fallback) ✓ Map each audio channel to interviewer or candidate ✓ Add diarisation as a fallback for mixed audio ✓ Keep overlapping speech as separate turns with their own timestamps ✓ Spot-check attribution accuracy on a test interview | 0 | 2.4 | 0.4 | 2.8
|  |  | Structured, timestamped transcript builder ✓ Merge results into ordered turns: turn ID, speaker, start, end, text ✓ Join short consecutive utterances from the same speaker ✓ Validate against the transcript schema ✓ Keep turn IDs stable so later analysis can cite them as evidence | 0 | 2 | 0.4 | 2.4
|  |  | Transcript persistence, retrieval, silence and overlap handling ✓ Save turns as they are finalised ✓ Add retrieval by session and an export endpoint ✓ Handle silence, noise and accents without failure; drop empty turns ✓ Delete raw audio once the transcript is produced (N16) | 0 | 2.4 | 0.8 | 3.2
|  | Live Display | Live transcript panel in interview room ✓ Push turns to the UI over WebSocket or SSE ✓ Show speaker labels and timestamps with auto-scroll ✓ Display interim text in a lighter style until finalised ✓ Show a degraded-state message if speech-to-text is unavailable | 2.4 | 0 | 0.4 | 2.8
6 | Post-Interview: Q&A Analysis & Consolidated Assessment - F5, F6 |  |  | 3.6 | 10 | 2.4 | 16
|  | Q&A Analysis (F5) | Question-answer pair segmentation (follow-ups, multi-part answers) ✓ Classify turns as question, answer, follow-up or other ✓ Pair each answer with the question that prompted it; merge multi-turn answers ✓ Handle clarifications and compound questions ✓ Store Q&A pairs with their turn IDs | 0 | 2.4 | 0.4 | 2.8
|  |  | Response evaluation (relevance, accuracy, completeness, articulation) with transcript-cited justification ✓ Score relevance, accuracy, completeness and articulation against a rubric ✓ Write a short justification quoting the supporting turn IDs ✓ Retry in the graph when output is invalid ✓ Persist evaluations per Q&A pair | 0 | 2.4 | 0.4 | 2.8
|  |  | Requirement coverage mapping and unexplored-requirement detection ✓ Map each Q&A pair to the job requirements it addresses ✓ Mark each requirement as covered, partially covered or unexplored ✓ List requirements never raised in the interview ✓ Persist the coverage map | 0 | 1.6 | 0.4 | 2
|  | Consolidated Assessment (F6) | Consolidation graph merging CV score, screening and interview analysis, with retry edges ✓ Build nodes: load CV score, load Q&A analysis, merge, generate summary, validate ✓ Keep explicit shared state with references to source evidence ✓ Add retry and error paths ✓ Output the assessment as structured JSON | 0 | 2.4 | 0.4 | 2.8
|  |  | Strengths, weaknesses, evidence gaps, recommended follow-up areas with traceability to CV or transcript ✓ Generate strengths, weaknesses, evidence gaps and recommended follow-up areas ✓ Link each conclusion to CV content or a transcript turn ✓ Present component scores rather than one opaque number ✓ State that the report supports, not replaces, the human decision | 0 | 0.8 | 0.4 | 1.2
|  |  | Assessment report view with PDF / HTML export ✓ Build the report page with sections for screening, scoring, interview and summary ✓ Make evidence links jump to the transcript turn ✓ Export to PDF or print-ready HTML ✓ Restrict access to interviewer role | 2.4 | 0.4 | 0.4 | 3.2
|  |  | Side-by-side candidate comparison for one role ✓ Select multiple assessed candidates for the same job ✓ Show component scores, strengths and gaps side by side ✓ Allow sorting by any component | 1.2 | 0 | 0 | 1.2
7 | Creative Feature - F11 |  |  | 4 | 9.6 | 2.4 | 16
|  | Innovation Feature | Identify real workflow gap, weigh alternatives, choose concept ✓ List 4-5 real workflow gaps not covered by F1-F10 ✓ Score each idea on value, feasibility, privacy risk and integration effort ✓ Choose one and record why the others were rejected ✓ Confirm it is not a variation of a listed feature | 0 | 1.2 | 0 | 1.2
|  |  | Write rationale document (300-500 words) in /docs ✓ Write 300-500 words: problem, who benefits, value, why prioritised over alternatives ✓ Commit to /docs | 0 | 1.2 | 0 | 1.2
|  |  | Design and implement the feature ✓ Define the data model, API and any graph changes ✓ Implement the backend logic ✓ Implement the UI ✓ Check it against privacy and fairness requirements | 4 | 4.8 | 0 | 8.8
|  |  | Integrate with platform and test on the 20 sample CVs ✓ Hook the feature into the existing candidate flow ✓ Run it on the 20 sample CVs and one mock interview ✓ Check core features for regressions ✓ Fix defects found | 0 | 1.6 | 2.4 | 4
|  |  | Document as 'Innovation Feature' in README ✓ Add an 'Innovation Feature' section: what it does, how to use it, limitations ✓ Add it to the demo script | 0 | 0.8 | 0 | 0.8
8 | Hardening & Optional Stretch |  |  | 2.4 | 4.4 | 1.2 | 8
|  | Hardening | Graceful error handling; no stack traces, paths or prompts leaked to client ✓ Add global exception handlers that return generic messages ✓ Return a clear error state when the LLM or speech service fails ✓ Test with invalid keys and the network off ✓ Make UI error messages understandable to non-technical users | 0 | 1.2 | 0.4 | 1.6
|  |  | Structured logging without personal data or secrets ✓ Emit JSON logs with request and job IDs ✓ Exclude names, contact details, transcript text and secrets ✓ Log key operations and all failures | 0 | 0.8 | 0 | 0.8
|  |  | Privacy controls: candidate deletion endpoint, data minimisation, fairness note ✓ Add an admin endpoint or script that deletes a candidate and all linked data ✓ Confirm raw audio is removed and only required data is stored ✓ Document external services receiving candidate data and what is sent (N18), plus retention ✓ Write the fairness note: no protected attributes used, known limitations | 0 | 1.6 | 0.4 | 2
|  |  | Input validation review and dependency pinning ✓ Review every API input for validation and size limits ✓ Pin dependency versions and remove unused packages ✓ Search the repo history for committed secrets or personal data | 0 | 0.8 | 0 | 0.8
|  |  | UI polish and progress indicators for long-running operations ✓ Add loading and progress states to long-running actions ✓ Rewrite error messages in plain language ✓ Apply the product name and branding consistently ✓ Walk through the app as a first-time user | 2.4 | 0 | 0.4 | 2.8
|  | Stretch (F7-F10) | Optional: attempt one stretch feature only if all core features are complete (not in baseline) ✓ Only if all six core features and F11 are complete, attempt one of F7-F10 ✓ Otherwise spend the time on hardening; excluded from baseline effort | 0 | 0 | 0 | 0
9 | Integration, Documentation & Submission |  |  | 2.4 | 8.4 | 5.2 | 16
|  | Verification | Full end-to-end test with all 20 sample CVs ✓ Run all 20 sample CVs through screening and record timing ✓ Run a mock interview from session creation to final assessment ✓ Restart the containers and confirm all data persists ✓ Log and fix defects found | 0 | 0.8 | 3.2 | 4
|  |  | Clean-machine Docker verification ✓ Clone the repo on a machine or VM with no cached images or dependencies ✓ Follow only the README and note any gap ✓ Verify start, stop and reset commands | 0 | 1.2 | 1.2 | 2.4
|  | Documentation | README, architecture diagram and LangGraph as-built description, privacy and data-handling note, updated WBS ✓ Complete every README section required by G2 ✓ Finalise the architecture diagram and describe the LangGraph design as built ✓ Write the privacy and data-handling note ✓ Update the WBS with planned versus actual effort and commit under /docs | 0 | 3.2 | 0 | 3.2
|  | Presentation & Release | Anonymise demo material, build slide deck, write demo script ✓ Replace real-looking names and details in screenshots and examples ✓ Build slides: problem, name and positioning, architecture, demo, innovation, lessons learned ✓ Write the demo script with a fallback for each step | 1.6 | 0.8 | 0 | 2.4
|  |  | Rehearse 20-30 minute presentation and live demo ✓ Time a full 20-30 minute run-through ✓ Prepare answers on graph topology, design decisions and limitations ✓ Prepare anonymised backup screenshots in case the live demo fails | 0.8 | 0.8 | 0 | 1.6
|  |  | Final freeze, tag release (v1.0-final), submit repo and present ✓ Freeze the code and fix only blocking bugs ✓ Confirm no secrets or personal data are in the repo ✓ Tag the release (v1.0-final) and submit the repository ✓ Deliver the presentation and demo | 0 | 1.6 | 0.8 | 2.4
|  |  | Total (man-hours) | 33.2 | 104.4 | 22.4 | 160
|  |  | Total (man-days) | 4.15 | 13.05 | 2.8 | 20